## Index
Delivery Governance Data Model — Master Clarity Table
Sheet Name | What it Aims to Do (Plain English) | Remember it as | Column Names (What’s Inside) | Data Nature
Process_Task_Dictionary | Defines how delivery should work — tasks, sequence, ownership, SLA, and visibility across the entire lifecycle | The Blueprint | Lifecycle_Stage, Task_ID, Task_Name, Task_Description, Input_Type, Standard_TAT_Hours, Default_Task_Owner, Hold_Applicable (Y/N), Escalation_Applicable (Y/N), Upstream_Task_ID, Customer_Visible (Y/N), Active_Flag (Y/N) | Lookup / Static (does not change per order)
Orders_Master | Provides one-line status per order so PMs and leaders can see where each order is and whether it is healthy | The Dashboard | Order_ID, Customer_Name, Customer_Type (SMB / Enterprise), Circle/Region, Lifecycle_Stage, Current_Task_ID, Order_Type (Wired / Wireless), Order_Start_Date, Order_Status, Overall_RAG, SLA_Breach_Flag | Transactional (Order-level)
Order_Task_Execution | Records what is actually happening on the ground — every task executed, by whom, with delays, holds, and escalations | The Work Log | Order_ID, Task_ID, Lifecycle_Stage, Assigned_To, Task_Status, Task_Start_Date, Actual_Hours, Hold_Reason_Code, Reassignment_Requested (Yes/No), Escalation_Triggered (Yes/No) | Transactional (Task-level, grows over time)
Hold_Reason_LOV | Standardizes why tasks are delayed, who is responsible, and expected impact — removes free-text ambiguity | The Excuse Dictionary | Hold_Code, Hold_Reason, Responsibility, Delayed_TAT, Category, Escalation_Matrix | Lookup / Static
Escalation_Matrix | Defines when and to whom issues are escalated, based on lifecycle and SLA breach duration | The Rulebook for Escalation | Lifecycle_Stage, SLA_Breach_Hours, Escalate_To, Escalated_Team | Lookup / Policy-driven
Process_Task_Dictionary (MASTER) - Defines the end-to-end delivery process blueprint — tasks, ownership, SLAs, dependencies, and system vs manual touchpoints. Acts as the single source of truth for how delivery should run, independent of any specific order.
Process_Task_Dictionary (MASTER) | Description (what it contains + type of input) |  |  |  | Themes
Lifecycle_Stage | Delivery lifecycle to which the task belongs (e.g., Lead to Order (L2O), Customer Onboarding, Build to Order (B2O), Last Mile Build – Wireless/Fiber, Order to Activation (O2A)) |  |  |  | Choose Theme...
Task_ID | Unique identifier for the task, used as the primary reference key across all sheets (e.g., L2O_01, B2O_05, O2A_09) |  |  |  | Location Strategy & Cost Efficiency
Task_Name | Business-friendly name of the task representing a discrete delivery activity (e.g., “WBS Creation”, “Device Installation at Site”) |  |  |  | Talent & Skills Capability
Task_Description | Short functional description explaining what the task does in business terms |  |  |  | Technology Adoption & Innovation
Input_Type | Indicates how the task is executed: System (automated via OSS/BSS) or Manual (email, coordination, human-driven) |  |  |  | Service Delivery & Operational Excellence
Standard_TAT_Hours | Baseline expected turnaround time for completing the task, expressed in hours |  |  |  | Global Integration & Strategic Alignment
Default_Task_Owner | Default role or team accountable for executing the task (e.g., Sales Ops, PMO, Field Ops, NOC) |  |  |  | Value Delivered to Enterprise
Hold_Applicable (Y/N) | Flag indicating whether the task can legitimately be put on HOLD (Y = allowed, N = not allowed)
Escalation Type | Auto or Manual
Upstream_Task_ID | Task_ID of the immediate predecessor task that must be completed before this task starts
Customer_Visible (Y/N) | Indicates whether this task or milestone is visible to the customer (Y = visible, N = internal only)
Active_Flag (Y/N) | Indicates whether the task is currently active in the delivery model (used for versioning and decommissioning)
Orders_Master - Provides a one-row snapshot per order showing where it is in the lifecycle and its overall health. Enables Program Managers and Leadership to track orders by exception and quickly identify risks.
Orders_Master | Description (what it contains + type of input)
Order_ID | Unique identifier for the customer order (one row per order)
Client_Name | Name of the enterprise customer placing the order
POC_name | Name of the person who will using the tool
Customer Ttype | Enterprise/SMB
Cricle/Region | Mention the Circle
Lifecycle_Stage | Current lifecycle stage of the order (L2O, B2O, Last Mile Build, O2A, Completed)
Current_Task_ID | Task_ID of the task currently in progress for the order
Order_Type | Type of order based on access technology: Wired (FTTx/Ethernet) or Wireless (UBR/FWA)
Order_Start_Date | Date on which the order entered the delivery lifecycle
Order_Status | Overall order state (In Progress, Completed, In Risk)
Overall_RAG | Overall health of the order derived from task-level SLAs (Green / Amber / Red)
SLA_Breach_Flag | Indicates whether any SLA breach has occurred on the order (Yes / No)
Order_Task_Execution - Captures real-time task execution data for each order — status, delays, holds, and escalations. Drives Ops inbox, SLA tracking, RAG calculation, reassignment, and escalation logic.
Order_Task_Execution | Description (what it contains + type of input)
Order_ID | Reference to the order against which the task is being executed
Task_ID | Reference to the task definition from Process_Task_Dictionary
Lifecycle_Stage | Lifecycle stage in which this task is executed (L2O, B2O, LMB, O2A)
Order_Type | Derived from Orders_Master to indicate Wired or Wireless execution context
Assigned_To | User, role, or team currently responsible for executing the task
Task_Status | Execution status of the task (Completed, In Progress, TBD, In Risk)
Task_Start_Date | Date/time when task execution started
Actual_Hours | Actual time spent so far (or total time taken) to execute the task
Hold_Reason_Code | Standardized hold reason code selected when a task is put on HOLD (from Hold_Reason_LOV)
Reassignment_Requested | Indicates whether reassignment has been requested by the assignee (Yes / No)
Escalation_Triggered | Indicates whether escalation has been triggered for this task (Yes / No)
Hold_Reason_LOV - Standardized list of allowed hold reasons with accountability, expected delay, and escalation guidance. Ensures delay reasons are structured, auditable, and analytically usable, eliminating free-text ambiguity.
Hold_Reason_LOV | Description (what it contains + type of input)
Hold_Code | Unique code representing a standardized hold reason (e.g., HR01, HR15)
Hold_Reason | Business-readable description explaining why the task is on HOLD
Lifecycle_Stage | Lifecycle where these Hold reasons fall in
Delayed_TAT | Expected delay caused by this hold reason (e.g., 24 Hrs, 72 Hrs, 7 Days, NA)
Category | Classification of delay type (Customer, Network, Construction, Commercial, System, External Dependency)
Escalation_Matrix - Defines who gets escalated and when, based on SLA breach thresholds at a lifecycle level. Enables time-based, consistent escalation without manual judgement or task-level noise.
Escalation_Matrix | Description (what it contains + type of input)
Lifecycle_Stage | Lifecycle stage to which the escalation rule applies (L2O, B2O, LMB – Wireless/Fiber, O2A)
SLA_Breach_Hours | Time threshold (in hours) beyond which escalation should be triggered
Escalate_To | Role to which the issue is escalated (Program Manager, Delivery Head)
Escalated_Team | Functional team expected to act on the escalation (Sales Ops, Construction, NOC, PMO)
Login Credentials for all personas along with the organization hierarchy
Login_Credentials | Description (what it contains + type of input)
Type | User role classification defining access scope within the system (e.g., Leadership, Program, Operations, Customer). Input type: predefined role value (text)
Login_ID | Unique user identifier used for authentication and login (typically an official email ID). Input type: text, unique
Password | User password used for login authentication (demo or encrypted in real implementation). Input type: text
Order_ID | Specific order mapped to the user (applicable mainly for Customer users; NA for others). Input type: Order reference or NA
POC_Name | Name of the user or point of contact associated with the login ID. Input type: text
Designation | User’s role or designation within the organization (e.g., PMO, Field Engineer, Manager). Input type: text
Reports to | Reporting manager or supervisory role for the user (used for hierarchy and escalation logic). Input type: text or NA
Team_Name | Team or functional unit the user belongs to (used to filter tasks and orders). Input type: predefined team name
Active_Flag | Indicates whether the login is active and allowed system access (Y/N). Input type: Y/N

## Process_Task_Dictionary
Lifecycle_Stage | Task_ID | Task_Name | Task_Description | Input_Type | Standard_TAT_Hours | Amber_Threshold_% | Red_Threshold_% | Default_Task_Owner | Hold_Applicable (Y/N) | Escalation Type | Upstream_Task_ID | Customer_Visible (Y/N) | Active_Flag (Y/N)
Lead to Order | L2O_01 | Primary Lead Creation | Capture and register the initial enterprise customer lead in the system. | System | 4 | 3.2 | 4 | Sales Ops | N | Manual | NA | N | Y
Lead to Order | L2O_02 | Secondary Lead Creation | Create supporting or downstream leads linked to the primary opportunity. | System | 4 | 3.2 | 4 | Sales Ops | N | Manual | L2O_01 | N | Y
Lead to Order | L2O_03 | Desktop RFS check | Validate service feasibility remotely using existing network data and records. | System | 8 | 6.4 | 8 | Network Planning | N | Manual | L2O_02 | N | Y
Lead to Order | L2O_04 | Last Mile Solution Type (FTTx, IP, UBR) Validation | Finalise the last-mile delivery solution based on feasibility and customer requirements. | System | 12 | 9.6 | 12 | Network Planning | N | Manual | L2O_03 | N | Y
Lead to Order | L2O_05 | Business Capex Approval based on BOQ & SOQ | Secure internal capital approval based on estimated build and material costs. | System | 24 | 19.2 | 24 | Finance / PMO | Y | Auto | L2O_04 | N | Y
Lead to Order | L2O_06 | Customer Proposal Submission | Submit the commercial and technical proposal to the customer for review. | System | 8 | 6.4 | 8 | Sales | N | Auto | L2O_05 | Y | Y
Lead to Order | L2O_07 | Customer Acceptance/Purchase Order(PO) | Receive formal customer acceptance and purchase order to proceed. | System | 24 | 19.2 | 24 | Sales | Y | Auto | L2O_06 | Y | Y
Customer Onboarding | COB_01 | CAF Creation | Create the Customer Application Form to initiate onboarding. | System | 4 | 3.2 | 4 | Sales Ops | N | Auto | L2O_07 | N | Y
Customer Onboarding | COB_02 | CF Creation | Generate the Customer Form capturing service and billing details. | System | 4 | 3.2 | 4 | Sales Ops | N | Auto | COB_01 | N | Y
Customer Onboarding | COB_03 | CF Approval | Validate and approve customer information for downstream processing. | System | 12 | 9.6 | 12 | PMO | Y | Auto | COB_02 | N | Y
Customer Onboarding | COB_04 | SAF Creation | Create the Service Activation Form to initiate service setup. | System | 4 | 3.2 | 4 | Sales Ops | N | Auto | COB_03 | N | Y
Customer Onboarding | COB_05 | SAF Submission | Submit the Service Activation Form to trigger provisioning workflows. | System | 4 | 3.2 | 4 | Sales Ops | N | Auto | COB_04 | N | Y
Build to Order | B2O_01 | RFS Check-Building RFS Validation | Confirm building readiness for service delivery and construction. | System | 8 | 6.4 | 8 | Network Planning | N | Manual | COB_05 | N | Y
Build to Order | B2O_02 | SharePoint Update for CPC release | Update project documentation to enable CPC and construction release. | Manual | 12 | 9.6 | 12 | PMO | Y | Auto | B2O_01 | N | Y
Build to Order | B2O_03 | ORN to Secondary Lead Tagging | Link the order reference number to secondary leads for tracking. | Manual | 12 | 9.6 | 12 | Sales Ops | Y | Auto | B2O_02 | N | Y
Build to Order | B2O_04 | SAP ID and WBS creation against customer ORN | Create SAP project and WBS structures for cost and execution tracking. | Manual | 24 | 19.2 | 24 | Finance | Y | Auto | B2O_03 | N | Y
Build to Order | B2O_05 | Scope release to Construction PMO | Hand over approved scope to the construction management team. | Manual | 12 | 9.6 | 12 | PMO | Y | Manual | B2O_04 | N | Y
Build to Order | B2O_06 | Scope Release to States for actual Last Mile Build | Release construction scope to regional or state execution teams. | System | 8 | 6.4 | 8 | PMO | N | Manual | B2O_05 | N | Y
Last Mile Build for Wireless (UBR/FWA) | LMB_WL01 | WBS Creation | Create work breakdown structure for wireless last-mile execution. | Manual | 12 | 9.6 | 12 | PMO | Y | Auto | B2O_06 | N | Y
Last Mile Build for Wireless (UBR/FWA) | LMB_WL02 | UBR LOS Survey | Conduct line-of-sight survey for wireless connectivity feasibility. | System | 24 | 19.2 | 24 | Field Ops | Y | Auto | LMB_WL01 | N | Y
Last Mile Build for Wireless (UBR/FWA) | LMB_WL03 | Solution Design Release | Finalise and release the wireless network design. | System | 12 | 9.6 | 12 | Network Engineering | N | Auto | LMB_WL02 | N | Y
Last Mile Build for Wireless (UBR/FWA) | LMB_WL04 | BoQ/SoQ Generation | Generate bill and schedule of quantities for wireless build. | System | 12 | 9.6 | 12 | Network Engineering | N | Auto | LMB_WL03 | N | Y
Last Mile Build for Wireless (UBR/FWA) | LMB_WL05 | UBR and IBD Construction | Execute wireless infrastructure and in-building deployment. | System | 72 | 57.6 | 72 | Field Ops | Y | Manual | LMB_WL04 | N | Y
Last Mile Build for Wireless (UBR/FWA) | LMB_WL06 | O&M HOTO | Hand over the deployed wireless network to operations and maintenance. | System | 8 | 6.4 | 8 | NOC | N | Manual | LMB_WL05 | N | Y
Last Mile Build for Wireless (UBR/FWA) | LMB_WL07 | Building RFS declaration | Declare the wireless site ready for service activation. | Manual | 8 | 6.4 | 8 | PMO | Y | Manual | LMB_WL06 | Y | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W01 | WBS Creation | Create work breakdown structure for fiber last-mile execution. | System | 8 | 6.4 | 8 | PMO | N | Auto | B2O_06 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W02 | Construction Survey-ISP | Conduct in-building survey for service provider infrastructure. | System | 24 | 19.2 | 24 | Field Ops | Y | Manual | LMB_W01 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W03 | Construction Survey-OSP | Conduct outside plant survey for external fiber routing. | System | 24 | 19.2 | 24 | Field Ops | Y | Manual | LMB_W02 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W04 | Construction Survey-IBD | Conduct in-building distribution survey for fiber layout. | System | 24 | 19.2 | 24 | Field Ops | Y | Manual | LMB_W03 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W05 | Design Release | Finalise and release detailed fiber network design. | System | 16 | 12.8 | 16 | Network Engineering | N | Manual | LMB_W04 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W06 | BoQ/SoQ Generation | Generate bill and schedule of quantities for fiber build. | System | 12 | 9.6 | 12 | Network Engineering | N | Manual | LMB_W05 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W07 | OSP Build | Execute outside plant fiber construction activities. | System | 72 | 57.6 | 72 | Field Ops | Y | Manual | LMB_W06 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W08 | IBD Build | Execute in-building fiber deployment. | System | 72 | 57.6 | 72 | Field Ops | Y | Manual | LMB_W07 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W09 | ISP Build | Complete service provider infrastructure setup. | System | 48 | 38.4 | 48 | Field Ops | Y | Manual | LMB_W08 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W10 | O&M HOTO | Hand over the fiber network to operations and maintenance. | System | 8 | 6.4 | 8 | NOC | N | Manual | LMB_W09 | N | Y
Last Mile Build for Fiber (FTTX/Ethernet) | LMB_W11 | Building RFS declaration | Declare fiber infrastructure ready for service activation. | System | 8 | 6.4 | 8 | PMO | N | Manual | LMB_W10 | Y | Y
Order to Activation | O2A_01 | Network Solution JEP Task validation | Validate network solution tasks in the enterprise portal. | System | 4 | 3.2 | 4 | NOC | N | Manual | LMB_W11 | N | Y
Order to Activation | O2A_02 | Network Solution Task closure | Close network solution validation tasks after approval. | System | 2 | 1.6 | 2 | NOC | N | Manual | O2A_01 | N | Y
Order to Activation | O2A_03 | Auto Sale Order (SO) Generated for material delivery | Automatically generate sales order for material delivery. | System | 2 | 1.6 | 2 | SAP / OSS | N | Auto | O2A_02 | N | Y
Order to Activation | O2A_04 | Installation Work Order(IWO) Generated | Create work order for installation activities. | System | 4 | 3.2 | 4 | Field Ops | N | Auto | O2A_03 | N | Y
Order to Activation | O2A_05 | Manual SO Creation for required Material | Manually create sales order where automation is not applicable. | System | 12 | 9.6 | 12 | Supply Chain | Y | Manual | O2A_04 | N | Y
Order to Activation | O2A_06 | Material Delivery SO Status | Track delivery status of ordered materials. | System | 24 | 19.2 | 24 | Supply Chain | Y | Manual | O2A_05 | N | Y
Order to Activation | O2A_07 | IWO Assigned | Assign installation work order to execution team or vendor. | System | 4 | 3.2 | 4 | Field Ops | N | Manual | O2A_06 | N | Y
Order to Activation | O2A_08 | Device/Consumable Issuance to Site engineer/Vendor | Issue required devices and consumables to field teams. | System | 8 | 6.4 | 8 | Warehouse | Y | Manual | O2A_07 | N | Y
Order to Activation | O2A_09 | Device Installation at Site | Install devices at the customer location. | Manual | 24 | 19.2 | 24 | Field Ops | Y | Manual | O2A_08 | N | Y
Order to Activation | O2A_10 | IWO Closure | Close installation work order upon completion. | System | 4 | 3.2 | 4 | Field Ops | N | Manual | O2A_09 | N | Y
Order to Activation | O2A_11 | Auto Service Provisioning completed | Automatically provision services on the network. | System | 2 | 1.6 | 2 | OSS / NOC | N | Manual | O2A_10 | N | Y
Order to Activation | O2A_12 | Device MOP available for manual provisioning | Provide method of procedure for manual provisioning if required. | System | 4 | 3.2 | 4 | NOC | N | Manual | O2A_11 | N | Y
Order to Activation | O2A_13 | Auto Service Testing Result | Execute and capture automated service testing results. | System | 2 | 1.6 | 2 | NOC | N | Auto | O2A_12 | N | Y
Order to Activation | O2A_14 | Test Work Order (TWO) Generated | Generate work order for service testing activities. | System | 2 | 1.6 | 2 | NOC | N | Auto | O2A_13 | N | Y
Order to Activation | O2A_15 | Test Work Order (TWO) Assigned | Assign test work order to execution team. | System | 4 | 3.2 | 4 | Field Ops | N | Auto | O2A_14 | N | Y
Order to Activation | O2A_16 | Service Testing with customer | Perform joint service testing with the customer. | Manual | 16 | 12.8 | 16 | NOC | Y | Auto | O2A_15 | Y | Y
Order to Activation | O2A_17 | Customer Acceptance document Signoff | Obtain formal customer signoff after successful testing. | System | 8 | 6.4 | 8 | Program Manager | Y | Auto | O2A_16 | Y | Y
Order to Activation | O2A_18 | TWO closure | Close test work order after completion. | System | 2 | 1.6 | 2 | NOC | N | Auto | O2A_17 | N | Y
Order to Activation | O2A_19 | NOC HOTO & Billing trigger | Hand over service to NOC and trigger billing activation. | System | 4 | 3.2 | 4 | NOC / Billing | N | Auto | O2A_18 | Y | Y

## Orders_Master
Order_ID | Client_Name | POC_Name | Customer Type | Order_Type | Circle/Region | Lifecycle_Stage | Current_Task_ID | Order_Start_Date | Order_Status | Overall_RAG | SLA_Breach_Flag
ORD_1001 | ABC Bank HQ | Alex | Enterprise | Wireless | Mumbai | Last Mile Build – Wireless | LMB_WL05 | 2025-09-01 | In Progress | Red | Yes
ORD_1002 | XYZ Pharma Plant | Barbara | Enterprise | Wired | Hyderabad | Last Mile Build – Fiber | LMB_W07 | 2025-08-25 | In Progress | Amber | No
ORD_1003 | FinServe Ltd | Cole | Enterprise | Wireless | Bengaluru | Order to Activation | O2A_09 | 2025-09-05 | In Progress | Red | Yes
ORD_1004 | RetailCorp DC | Dom | SMB | Wired | Pune | Order to Activation | O2A_16 | 2025-08-20 | In Progress | Amber | No
ORD_1005 | TechPark SEZ | Eleanor | SMB | Wired | Chennai | Completed | O2A_19 | 2025-08-01 | Completed | Green | No

## Order_Task_Execution
Order_ID | Task_ID | Lifecycle_Stage | Assigned_To | Task_Status | Task_Start_Date | Actual_Hours | Hold_Reason_Code | Reassignment_Requested | Escalation_Triggered
ORD_1001 | LMB_WL01 | Last Mile Build – Wireless | PMO_User_01 | Completed | 2025-09-01 | 14 | NA | No | No
ORD_1001 | LMB_WL02 | Last Mile Build – Wireless | FieldOps_03 | Completed | 2025-09-02 | 28 | HR02 | No | Yes
ORD_1001 | LMB_WL03 | Last Mile Build – Wireless | NetEng_01 | Completed | 2025-09-03 | 12 | NA | No | No
ORD_1001 | LMB_WL04 | Last Mile Build – Wireless | NetEng_01 | Completed | 2025-09-04 | 14 | NA | No | No
ORD_1001 | LMB_WL05 | Last Mile Build – Wireless | FieldOps_04 | In Progress | 2025-09-05 | 96 | HR08 | Yes | Yes
ORD_1002 | LMB_W01 | Last Mile Build – Fiber | PMO_User_01 | Completed | 2025-08-25 | 8 | NA | No | No
ORD_1002 | LMB_W02 | Last Mile Build – Fiber | FieldOps_01 | Completed | 2025-08-26 | 26 | HR01 | No | No
ORD_1002 | LMB_W03 | Last Mile Build – Fiber | FieldOps_01 | Completed | 2025-08-27 | 24 | NA | No | No
ORD_1002 | LMB_W04 | Last Mile Build – Fiber | FieldOps_02 | Completed | 2025-08-28 | 25 | HR07 | No | No
ORD_1002 | LMB_W05 | Last Mile Build – Fiber | NetEng_01 | Completed | 2025-08-30 | 18 | NA | No | No
ORD_1002 | LMB_W06 | Last Mile Build – Fiber | NetEng_01 | Completed | 2025-09-01 | 12 | NA | No | No
ORD_1002 | LMB_W07 | Last Mile Build – Fiber | FieldOps_02 | In Progress | 2025-09-02 | 78 | NA | No | No
ORD_1003 | O2A_07 | Order to Activation | FieldOps_02 | Completed | 2025-09-05 | 4 | NA | No | No
ORD_1003 | O2A_08 | Order to Activation | Warehouse_01 | Completed | 2025-09-06 | 8 | NA | No | No
ORD_1003 | O2A_09 | Order to Activation | FieldOps_03 | In Progress | 2025-09-07 | 36 | HR10 | No | Yes
ORD_1004 | O2A_14 | Order to Activation | NOC_01 | Completed | 2025-08-20 | 2 | NA | No | No
ORD_1004 | O2A_15 | Order to Activation | FieldOps_01 | Completed | 2025-08-21 | 4 | NA | No | No
ORD_1004 | O2A_16 | Order to Activation | NOC_02 | In Progress | 2025-08-22 | 20 | HR04 | No | No
ORD_1005 | O2A_16 | Order to Activation | NOC_01 | Completed | 2025-08-01 | 14 | NA | No | No
ORD_1005 | O2A_17 | Order to Activation | PMO_User_01 | Completed | 2025-08-02 | 8 | NA | No | No
ORD_1005 | O2A_18 | Order to Activation | NOC_01 | Completed | 2025-08-03 | 2 | NA | No | No
ORD_1005 | O2A_19 | Order to Activation | Billing_01 | Completed | 2025-08-04 | 4 | NA | No | No

## Hold_Reason_LOV
Hold_Code | Hold_Reason | Lifecycle_Stage | Delayed_TAT | Category
HR01 | Activation failure | Order to Activation | 4 Days | System
HR02 | Authorised personnel not available | Any | NA | Resource
HR03 | Customer not interested | Lead to Order | 7 Days | Customer
HR04 | Customer reschedule | Any | 24 Hrs | Customer
HR05 | Documents pending | Lead to Order | NA | Customer
HR06 | Door lock | Last Mile Build – Wireless / Fiber | 72 Hrs | Customer Premises
HR07 | Electricity not available | Last Mile Build – Wireless / Fiber | 7 Days | External Dependency
HR08 | Engineer reschedule | Last Mile Build – Wireless / Fiber | 15 Days | Resource
HR09 | External wiring issue | Last Mile Build – Fiber | 15 Days | Infrastructure
HR10 | Inside home wiring / cabling issue | Last Mile Build – Wireless / Fiber | 24 Hrs | Customer Premises
HR11 | Logical connectivity failure | Order to Activation | 7 Days | Network
HR12 | Material not available at JC | Build to Order | 24 Hrs | Supply Chain
HR13 | Name & address validation | Customer Onboarding | 72 Hrs | Customer Data
HR14 | No / low power at S2 | Last Mile Build – Wireless / Fiber | 15 Days | Infrastructure
HR15 | OTB required | Build to Order | 15 Days | Infrastructure
HR16 | OTB required – all 4 ports full | Build to Order | 15 Days | Capacity
HR17 | OTB required – cable length >80m | Last Mile Build – Wireless | 7 Days | Infrastructure
HR18 | OTB required – cable routing <80m | Build to Order | 15 Days | Infrastructure
HR19 | OTB required – land owner objection | Build to Order | 15 Days | Regulatory / External
HR20 | OTB required – routing / road crossing | Build to Order | 15 Days | Regulatory / External
HR21 | OTB shifting – land owner objection | Build to Order | 24 Hrs | Regulatory / External
HR22 | Payment not received | Customer Onboarding | 24 Hrs | Commercial
HR23 | Device dead on arrival | Order to Activation | NA | Hardware
HR24 | Port / PON port issue | Order to Activation | 48 Hrs | Network
HR25 | Refuse to pay charges | Customer Onboarding | 24 Hrs | Commercial
HR26 | S2 capacity full | Last Mile Build – Fiber | NA | Capacity
HR27 | S2 ID mismatch | Order to Activation | 48 Hrs | Data Issue
HR28 | S2 label missing | Order to Activation | 48 Hrs | Data Issue
HR29 | Sales commitment issues | Lead to Order | 24 Hrs | Commercial
HR30 | Services not started | Order to Activation | 24 Hrs | Provisioning
HR31 | Slow speed / unable to browse | Order to Activation | 24 Hrs | Performance
HR32 | Society permission required | Build to Order | 24 Hrs | Regulatory / External
HR33 | System / application issue | Any | NA | System
HR34 | Voice not provisioned / Centrex not working | Order to Activation | 24 Hrs | Service Quality

## Escalation_Matrix
Lifecycle_Stage | SLA_Breach_Hours | Escalation_Level | Escalated_To_Name | Escalated_To_Login | Escalated_Team | Escalation_Role
Lead to Order | 12 | Level 1 | Steve.har | steve.har@telcotoday.com | OPS_L2O | Ops Manager
Lead to Order | 24 | Level 2 | Jason.y | jason.y@telcotoday.com | Program Lead_01 | Program Lead
Customer Onboarding | 12 | Level 1 | Dustin.hen | dustin.hen@telcotoday.com | OPS_ONBOARDING | Ops Manager
Customer Onboarding | 24 | Level 2 | Paul.p | paul.p@telcotoday.com | Program Lead_03 | Program Lead
Build to Order | 24 | Level 1 | Lucas.sin | lucas.sin@telcotoday.com | Operations_Build to Order | Ops Manager
Build to Order | 48 | Level 2 | Jason.y | jason.y@telcotoday.com | Program Lead_01 | Program Lead
Last Mile Build – Wireless | 48 | Level 1 | Max.mad | max.mad@telcotoday.com | Operations_Last Mile Build Wireless | Ops Manager
Last Mile Build – Wireless | 72 | Level 2 | Simon.c | simon.c@telcotoday.com | Program Lead_02 | Program Lead
Last Mile Build – Fiber | 72 | Level 1 | Will.kol | will.kol@telcotoday.com | Operations_Last Mile Build Wired | Ops Manager
Last Mile Build – Fiber | 120 | Level 2 | Simon.c | simon.c@telcotoday.com | Program Lead_02 | Program Lead
Order to Activation | 12 | Level 1 | Mike.dor | mike.dor@telcotoday.com | Operations_Order to Activation | Ops Manager
Order to Activation | 24 | Level 2 | Paul.p | paul.p@telcotoday.com | Program Lead_03 | Program Lead

## Login_Credentials
Type | Login_ID | Password | Order_ID | POC_Name | Designation | Reports to | Team_Name | Active_Flag
Customer | walter.white@abc.com | walter.white@123 | ORD_1001 | Walter.white | NA | NA | ABC Bank HQ | Y
Customer | jessie.pinkman@xyz.com | jessie.pinkman@223 | ORD_1002 | Jessie.pinkman | NA | NA | XYZ Pharma Plant | Y
Customer | saul.goodman@finserve.com | saul.goodman@323 | ORD_1003 | Saul.goodman | NA | NA | FinServe Ltd | Y
Customer | hank.schrader@retailcorp.com | hank.schrader@423 | ORD_1004 | Hank.schrader | NA | NA | RetailCorp DC | Y
Customer | gus.fring@techpark.com | gus.fring@523 | ORD_1005 | Gus.fring | NA | NA | TechPark SEZ | Y
Leader | sam.jackson@telcotoday.com | sam.jackson@623 | NA | Sam.jackson | Leadership | NA | Leadership | Y
Operations | steve.har@telcotoday.com | steve.har@723 | NA | Steve.har | Manager_Lead to Order | Jason.y | OPS_L2O | Y
Operations | rohan.gupta@telcotoday.com | rohan.gupta@823 | NA | Rohan.Gupta | KAM_L2O | Steve.har | OPS_L2O | Y
Operations | anjali.mehra@telcotoday.com | anjali.mehra@923 | NA | Anjali.Mehra | KAM_L2O | Rohan.Gupta | OPS_L2O | Y
Operations | dustin.hen@telcotoday.com | dustin.hen@1023 | NA | Dustin.hen | Manager_Customer Onboarding | Paul.p | Operations_Customer Onboarding | Y
Operations | sneha.iyer@telcotoday.com | sneha.iyer@1123 | NA | Sneha.Iyer | KAM_Onboarding | Dustin.hen | OPS_ONBOARDING | Y
Operations | mohit.jain@telcotoday.com | mohit.jain@1223 | NA | Mohit.Jain | KAM_Onboarding | Sneha.Iyer | OPS_ONBOARDING | Y
Operations | lucas.sin@telcotoday.com | lucas.sin@1323 | NA | Lucas.sin | Manager_Build to Order | Jason.y | Operations_Build to Order | Y
Operations | karthik.rao@telcotoday.com | karthik.rao@1423 | NA | Karthik.Rao | Delivery Lead | Lucas.sin | OPS_B2O | Y
Operations | neelam.singh@telcotoday.com | neelam.singh@1523 | NA | Neelam.Singh | Delivery Lead | Karthik.Rao | OPS_B2O | Y
Operations | max.mad@telcotoday.com | max.mad@1623 | NA | Max.mad | Manager_Last Mile Build Wireless | Simon.c | Operations_Last Mile Build Wireless | Y
Operations | arjun.malhotra@telcotoday.com | arjun.malhotra@1723 | NA | Arjun.Malhotra | Analyst | Max.mad | OPS_WL_SURVEY | Y
Operations | priti.kulkarni@telcotoday.com | priti.kulkarni@1823 | NA | Priti.Kulkarni | Analyst | Arjun.Malhotra | OPS_WL_SURVEY | Y
Operations | suresh.nair@telcotoday.com | suresh.nair@1923 | NA | Suresh.Nair | Field Engineer | Priti.Kulkarni | OPS_WL_BUILD | Y
Operations | deepa.menon@telcotoday.com | deepa.menon@2023 | NA | Deepa.Menon | Field Engineer | Suresh.Nair | OPS_WL_BUILD | Y
Operations | will.kol@telcotoday.com | will.kol@2123 | NA | Will.kol | Manager_Last Mile Build Wired | Simon.c | Operations_Last Mile Build Wired | Y
Operations | rahul.verma@telcotoday.com | rahul.verma@2223 | NA | Rahul.Verma | Analyst | Will.kol | OPS_FIBER_SURVEY | Y
Operations | nisha.kapoor@telcotoday.com | nisha.kapoor@2323 | NA | Nisha.Kapoor | Analyst | Rahul.Verma | OPS_FIBER_SURVEY | Y
Operations | vinod.sharma@telcotoday.com | vinod.sharma@2423 | NA | Vinod.Sharma | Field Engineer | Nisha.Kapoor | OPS_FIBER_BUILD | Y
Operations | kavita.desai@telcotoday.com | kavita.desai@2523 | NA | Kavita.Desai | Field Engineer | Vinod.Sharma | OPS_FIBER_BUILD | Y
Operations | mike.dor@telcotoday.com | mike.dor@2623 | NA | Mike.dor | Manager_Order to Activation | Paul.p | Operations_Order to Activation | Y
Operations | ramesh.patil@telcotoday.com | ramesh.patil@2723 | NA | Ramesh.Patil | Field Engineer | Mike.dor | OPS_INSTALL | Y
Operations | sunita.roy@telcotoday.com | sunita.roy@2823 | NA | Sunita.Roy | Field Engineer | Ramesh.Patil | OPS_INSTALL | Y
Operations | manish.khanna@telcotoday.com | manish.khanna@2923 | NA | Manish.Khanna | CFM | Sunita.Roy | OPS_BILLING | Y
Operations | ritu.arora@telcotoday.com | ritu.arora@3023 | NA | Ritu.Arora | CFM | Manish.Khanna | OPS_BILLING | Y
Program | jason.y@telcotoday.com | jason.y@3123 | NA | Jason.y | Program Lead | Sam.jackson | Program Lead_01 | Y
Program | simon.c@telcotoday.com | simon.c@3223 | NA | Simon.c | Program Lead | Steve.har | Program Lead_02 | Y
Program | paul.p@telcotoday.com | paul.p@3323 | NA | Paul.p | Program Lead | Rohan.Gupta | Program Lead_03 | Y